## Intro & Info
🌱 THE ECO-UTOPIA PARTY — Organizer Reference
Working date | 2026-11-28
Guest cap | Targeting roughly 200–300
Spaces (draft) | Ground floor + Tuinzaal for certain; likely also kitchen, a bedroom, washing machine room, kinderkamer. Roof/upper floors ruled out for security.
Entry concept (draft) | Two possible entrances under discussion: front door (main “processing” moment) + garage (immersive secondary route). Not finalized — needs a physical barrier to actually work.
Build / Strike | Friday/Saturday build + Sunday strike
Ruling party name (draft) | “PVV — Partij voor de Volgzaamheid” (recruitment poster already made) — open to change, see the design committee's working doc
🔗 Coordination hub
Shared Google Drive | https://drive.google.com/drive/u/0/folders/1GYWisgYVA5ZbZbp2zCoOdyWtf1lk7gzo
Organizers' Signal group | https://signal.group/#CjQKIF9T3735XddZ86fxpk2njMPfCbg8IfL1jrWZC4FajCQFEhB0F77-wumUdKZiyCtmayKj
Jack has only added people who seem to want to be more involved to the organizers' Signal group so far — others get added later. The party-facing group is a placeholder for now — expect it to be swapped for a fresh one once the save-the-date/propaganda push goes out.
Public / party-facing Signal group (placeholder) | https://bit.ly/4hEKvvp
Calendar Link | https://bit.ly/4Axrpir
🔒 This workbook is for ORGANIZERS ONLY
It contains secret-mechanic details (the resistance track, mole seeding, elite selection logic) that must not reach guests before the party. A separate, spoiler-free guest-facing doc gets built later once the concept is locked — the way Embers kept its guest checklist in this same tab, this one deliberately does not. Note: the ministries/factions, economy, and propaganda/costume design itself is being worked out by a small design committee (Jack, Chris, Wout) in a separate doc, not tracked in this shared workbook — ask Jack for the latest version.
✨ Concept snapshot
Humanity solved the climate crisis by becoming an authoritarian eco-fascist state, and it worked. Guests arrive as citizens of this regime and are meant to feel the seduction of an effective authoritarian system before confronting what it costs, then discover a secret revolution whose alternative governance turns out to be genuinely harder to run sustainably. Not “fascism is bad” — the point is making people feel the tradeoff between freedom and enforced collective outcomes. Tone: darkly funny, absurd, theatrical — not a lecture.
🎭 Emotional arc (7 stages)
1. This is hilarious (absurd propaganda)
2. Wait, this is actually fun (competing for status)
3. Oh shit, I'm participating in this (enforcing rules on others, enjoying privilege)
4. Maybe the system isn't entirely wrong (visible sustainability results)
5. There's another way (revolution surfaces, guests defect and sacrifice everything)
6. Oh, this is much harder (revolutionary governance struggles)
7. What would I actually choose (left with the question, not an answer)
📋 Organizer checklist
☐ Join the organizers' Signal group
☐ Read the concept doc and the Sept 9 kickoff meeting notes
☐ Take a role on the Roles tab
☐ Running an activity or experience? Add it to the Activities & Experiences tab
Related docs
• Eco-Fascist Party — Concept Development
• De Warren — Party Planning Reference
• Kickoff meeting notes — Sept 9, 2026
• Party Design — Committee Working Doc (ministries, economy, propaganda)

## Supplies & Offerings
Item | Category | Brought by | Quantity / notes
e.g. Beer | Drinks | Your name here | 1 crate
e.g. Snacks to share | Food | Your name here
e.g. Propaganda print materials | Props & Costume | Your name here
e.g. Something to gift | Gifting / other | Your name here | Trick, toy, game, anything to give away

## Shifts
🛠️ SHIFT TEAMS — what each one does
Team | What they do
Build | Help set up the party spaces on build day. Sign up below with roughly when you'll show up.
Bar | Staff the bar, serve food and drinks, keep the offerings table stocked and tidy.
Safety patrol | Walk the venue on a regular loop, watch for anything unsafe, follow the safety lead's brief.
Medical on-call | With medical training — be available if medical support is needed.
Shit Ninjas | (Everyone) take care of the toilet.
Welcome / Processing | Run the entry “processing” moment, greet people at the door and/or garage, get a rough headcount.
Sound cue crew | Trigger and run the announcement/speech audio through the night — installed by the sound & audio lead, staffed here.
Photography / Documentation | Cover the night in photos/video — for the archive afterward, and optionally as in-fiction “the state is watching” texture.
Strike | Full clean up and Leave No Trace check the next day. Sign up below with roughly when you'll show up.
🧱 BUILD SIGNUP |  |  | 🧹 STRIKE SIGNUP
Slot # | Name | Roughly what time you'll join |  | Slot # | Name | Roughly what time you'll join
1 |  |  |  | 1
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
5 |  |  |  | 5
6 |  |  |  | 6
7 |  |  |  | 7
8 |  |  |  | 8
9 |  |  |  | 9
10 |  |  |  | 10
11 |  |  |  | 11
12 |  |  |  | 12
13 |  |  |  | 13
14 |  |  |  | 14
15 |  |  |  | 15

## Activities & Experiences
Activity / Experience | Host | Time slot | Location | Description | Status
e.g. Carbon Audit checkpoint | Your name here | 8:30pm | Woonzaal | A short interactive station where citizens audit each other's consumption. | Pitched
Unbirth / hypnotic welcoming moment | Inge (+ Lexi?) |  | Garage | Floated at the Sept 9 kickoff — details still with Inge, wants to own this end-to-end. | Idea
Hanna?

## Music
DJ / act | Time slot | Genre / vibe | Equipment needed | Contact | Status
Note: the technical lead will confirm what sound/lighting equipment is actually available before DJs assume they need to bring their own gear.
e.g. Jack B2B Sam | 9pm–11pm | Warm-up, groovy house | 2 CDJs, mixer, own headphones | Your name here | Confirmed
Wout & Thijs project? | TBD | Floated as fitting the theme — possibly the “revolution” moment musically | TBD | Wout, Thijs | Idea

## Roles
Category | Role | Description | Priority | Signed up (name)
Multiple people can co-lead any role — list everyone in “Signed up.”
PRACTICAL ROLES
Practical | Coordinator & Party Production lead | Overall owner of the event. Final call on anything unresolved. | Must have | Jack, Irena
Practical | Propaganda & Marketing lead | Owns comms channels and messaging strategy — Signal groups, Discord, what goes out and when. (Distinct from the Propaganda & Visual Design lead below, who owns the actual visual assets.) | Must have | Jack, Chris
Practical | Safety lead | Writes the safety plan and briefs the safety patrol. | Should have
Practical | Sweep | Final walk-through of common spaces for drugs/hazards once the party's over. | Everyone still there at close — not a claimed role
Practical | Neighbourhood lead | Handles the door-knock, printed note, on-call contact for neighbour issues. | Must have
Practical | Volunteer coordinator | Builds the shift schedule, chases gaps across the Roles and Shifts tabs so nothing sits unfilled. | Should have | Winona
Practical | Technical lead | Sound/lighting/electronics setup, equipment point of contact. | Should have | Bart, Wout
Practical | Lighting lead | Sorts lighting for all spaces, including wind-down hours. | Nice to have
Practical | Decoration lead | Sets the look and feel, coordinates who brings what to decorate with. | Nice to have | Thijs?, Hanna?
Practical | Print lead | Prints signs: toilet, welcome info, shifts, schedules. | Should have
Practical | Finance lead | Tracks spend across costumes, the totem build, printing, sound production, and anything else the design committee needs to buy. | Should have | Jack
| Government lead | helps make the actor roles that run the party |  | Kim
| Bar lead |  |  | hanna
Food lead
Practical | Sound & audio lead | Builds the announcement/speech audio and installs it. | Should have | Bart, Wout (interested)
CREATIVE / CONCEPT ROLES
Creative | Storytelling / narrative lead | Owns the overarching story and how it's told through the night. | Must have | Chris
Creative | Propaganda & Visual Design lead | Posters, signage, visual language — the actual assets, as opposed to the comms strategy above. | Must have | Chris, Marina
Creative | Economy & Game Design lead | Owns the PC/footprint economy — the small design committee. | Must have | Jack, Chris, Wout
Creative | Costume & uniform lead | Sorts uniforms/costumes for elites, guards, ministries. | Should have | Kim
Creative | Activities & Performances coordinator | Owns coordinating everything on the Activities & Experiences tab — what's running, where, and when. | Must have | Jack (external), Kim (internal)
REACHED OUT / MENTIONED — NO ROLE YET
Name |  | Notes | Status
Winona |  | Said yes when asked to join; also part of the original recruitment DM batch —-> took the role of volunteer coordinator | Interested
Kim |  |  | Interested
Irene |  | Wants to be involved and expected to bring her own ideas; not yet looped in now that the date is close | Interested
Hanna |  | Floated as a possible voice actor for the announcement audio | Interested
Jacob-Jan (+ partner Jonas) |  | Said yes when asked to join, with his partner Yonas; also part of the original recruitment DM batch, and has a workshop idea with Joris from the kickoff | Wants to help later
Julia |  | Wants to host an activity; Jack's friend, not a De Warren resident | Interested
Thijs |  | Also part of the original recruitment DM batch; his music project with Wout was floated for the party | Interested
Lexi |  | Possible collaborator on Inge's activity; waiting to hear the date before confirming | Interested, pending date
Joey |  | Jack flagged wanting to ask if he'd like to contribute (Sept 10) | Interested
Other Burners (general) |  | Jack wants to ask more broadly within the Burner community — no specific names yet | Not yet asked
Suus |  |  | Not interested
Sam |  | Sitting on the sideline for now | Wants to help later
Anniek |  | Sitting on the sideline for now | Wants to help later
Victorine (Vliegmachine) |  | Sent the original recruitment DM with the Continuity Party poster | Interested
Chandar |  | Sent the original recruitment DM with the Continuity Party poster | Music lead
Pepijn |  | Sent the original recruitment DM with the Continuity Party poster | Help with buildup the days before |  | Infrastucture / deco
kees |  | Sent the original recruitment DM with the Continuity Party poster | Reached out — no response yet
Merel |  | Sent the original recruitment DM with the Continuity Party poster | Not interested
Lucas |  | Sent the original recruitment DM with the Continuity Party poster; Jack also flagged wanting to follow up with him directly (Sept 10) | Not interested
Graci |  | Sent the original recruitment DM with the Continuity Party poster | Interested, pending date
Daniela |  |  | Not interested
Joey |  |  | Interested
Kuba |  |  | Not interested
Toon |  |  | Not interested
Just |  |  | Not interested
Margo |  |  | Interested
ZeeZeey |  |  | Interested
Julia |  |  | Interested

## To-Do
Task | Owner | Due date | Status | Notes
Pick a date (Nov 21 or Nov 28) | Jack | ASAP | Open | Poll other organizers first, then lock it in
Swap the placeholder party-facing Signal group for a real one when the save-the-date goes out | Jack | Before save-the-date push | In progress | Placeholder link already live — see Intro & Info
First save-the-date propaganda poster | Chris, Marina | Before next meeting | Open
Set next meeting, two weeks out | Jack | ASAP | Open
Ask joey, lucas, and other Burners if they want to contribute |  |  | Open | See Roles tab — Reached out / mentioned section
Loop in Lexi — confirm he's on board |  | Once date is set | Open
Loop in Irene |  | Once date is set | Open | Expected to bring her own ideas
Follow up with Jacob-Jan and Jonas on their workshop idea |  |  | Open
Decide what scale/spaces to propose to the house |  |  | Open | De Warren residents need to sign off
Resolve core economy model (earn-up vs. start-in-debt) | Jack, Chris, Wout | Before building activities | Open | Design committee — see the Party Design working doc
Find a British-voiced volunteer for the announcement audio |  |  | Open | Bah or Hannah floated
Decide on the in-universe ruling party name |  |  | Open | PVV vs. an alternative
Make some stamps for the ministries | Chris